| Social Availability Strategy |  |  |
| --- | --- | --- |
| Components | Actions | Visibility |
| Social Host Ordinance (SHO)- new Leader: IPS Other policies: | - Publicize SHO – Spring 2013 - Provide training to PD - Presentations to high schools - Letters to parents - Promote on college campus - Create policy brief | Create messaging on components of the SHO that target parents, youth, college students and general population |
| Nuisance party enforcement Leader: Redlands PD Resources required for 10 party operations - Approximate cost: 8K | - High school parties – 5 operations p/y - Graduation time (2) - Homecoming (3) HS - College parties – 5 operations p/y - Start of school (1) - Greek allowed alcohol (1) - Halloween (1)? - St. Patrick’s Day (1)? - Cinco de Mayo (1)? | Provide general messaging about HS party enforcement around specific high risk times (a and b) and promote timely visibility prior to operations Develop visibility partners at U of R to reach college students with extra visibility efforts prior to nuisance patrols |
| DUI enforcement Leader: Redlands PD OTS Grant for 23 DUI operations | - Highly visible DUI enforcement aligned with nuisance party enforcement - Roadside DUI check Points (4) - Saturation patrols (6) | Use “Zero Tolerance” focus for underage drivers and promote timely high visibility surrounding all DUI operations aimed at specific targets audiences |
| Retail Availability Strategy |  |  |
| Deemed Approved Ordinance (DAO) Leader: IPS Other policies: | - Support passage of DAO - Develop media campaign - Build community support for DAO - Provide training to PD when passed - Create a policy brief - Educate city council | Implement a media campaign in support of DAO and organize community groups in support of the ordinance |
| DUI enforcement Leader: Redlands PD OTS grant for 23 DUI operations | - Highly visible DUI enforcement in the vicinity of the downtown bar area - Roadside DUI check points (6) - Saturation patrols (6) | Create DUI enforcement messages focused on the downtown bar area. Develop innovative ways to reach young adults from the campus and outside the City of Redlands aligned with the DUI enforcement |
| Responsible Beverage Service (RBS) training Leader: IPS | - Build support with the downtown bars managers to send staff to RBS training - PD RBS training - IPS – RBS training - SB Public health RBS training assistance | Publicize RBS training to all on-site alcohol licenses in Redlands Option: Develop a community / Downtown group (bars and businesses) to improve safety in the business district Survey of downtown bars |
| Compliance checks Leader: Redlands PD ABC Grant $7500 | - Decoy operations - Other? | Post operation publicity opportunities |