**WORK PLAN**

**April 1, 2013 – March 31, 2014**

**Reduce Underage and Excessive Drinking in 12 – 25 Year old Age Range**

***GOAL 1 – Reduce Retail Availability of Alcohol to Youth***

|  |  |  |  |
| --- | --- | --- | --- |
| **ACTIVITY** | **NUMBER PER YEAR** | **RESPONSIBLE PARTY** | **IMPLEMENTATION DATE** |
| Retail beverage seller/server training | 1 (minimum of 50 participants will be trained) | IPS/SMPD | By October, 31 2013 |
| Compliance checks | 16 (10 will be in kind) | SMPD | By 3/31/2014 (depending on officer availability and date we can provide subcontract from IPS to SMPD) |
| Visibility of Compliance Checks | 3 | IPS in collaboration with SMPD - still negotiating with SMPD on this – hope to increase significantly | By 3/31/2014 |
| Promote Deemed Approved Ordinance | 1 | IPS | TBD |

***GOAL 2 - Reduce Social Availability of Alcohol to Youth***

|  |  |  |  |
| --- | --- | --- | --- |
| **ACTIVITY** | **NUMBER PER YEAR** | **RESPONSIBLE PARTY** | **IMPLEMENTATION DATE** |
| Party Patrol | 2 | SMPD | TBD |
| Visibility of Party Patrols | TBD | IPS in collaboration with SMPD – still negotiating with SMPD on this | 3/31/2014 |
| Visibility of Social Host Liability | 1 | IPS | 3/31/2014 |
| Promote social host ordinance | 1 | IPS (in kind from LA County, SAPC funding) | TBD |

***GOAL 3 – Reduce Drinking and Driving***

|  |  |  |  |
| --- | --- | --- | --- |
| **ACTIVITY** | **NUMBER PER YEAR** | **RESPONSIBLE PARTY** | **IMPLEMENTATION DATE** |
| DUI Checkpoints | 4 | SMPD (in kind) | Quarterly (Two already completed two more to be completed Dec. 2013 and Mar. 2014) |
| Saturation Patrols | - | - | - |
| Visibility of DUI checkpoints | 4 | IPS in collaboration with SMPD, Traffic Division (still negotiating with SMPD on this - SMPD participation in kind) | Quarterly |
| Visibility of Saturation Patrols | - | - | - |
| Implement place of last drink (POLD) survey (this will include the development of a survey tool, administration of survey, analysis of survey results, annual report on survey results, and communication with SMPD about survey results) | # of surveys collected TBD | IPS/CLARE (Collaboration with CLARE - treatment provider - to implement surveys in DUI classes will be provided as in kind from La County SAPC funding) | 3/31/2014 |