WORK PLAN

April 1,.2013 – March 31, 2014

Redlands – Reduce Underage and Excessive Drinking in 12 – 25 Year old Age Range

GOAL #1 – Reduce Retail Availability

| ACTIVITY | NUMBER PER YEAR | RESPONSIBLE PARTY | IMPLEMENTATION DATE |
| --- | --- | --- | --- |
| DUI Enforcement Office of Traffic Safety (OTS) grant funds 23 Driving Under the Influence (DUI) operations (see below) (only 22 listed in plan) |  | Redland Police Department (RPD) | For the SPF SIG we have split the DUI operations between the downtown bar area and underage parties – High School (HS) and University of Redlands (U of R) |
| Saturation patrols - OTS 6 Downtown 6 Aligned with party enforcement | 6 of 12 | RPD | Targeted at identified dates in downtown area – 3 per quarter |
| DUI Checkpoints - OTS 6 Downtown 4 aligned with party enforcement | 6 of 10 | RPD | Targeted at identified dates in downtown area – 2 or 3 per quarter |
| DUI Visibility | 22 | RPD/Institute for Public Strategies (IPS) | Timely visibility prior to DUI operations: - Work with local bars to get DUI messages on their websites - Develop media pieces on DUI enforcement (social media, phone applications, print media and online media) |
| Compliance checks: Department of Alcoholic Beverage Control (ABC) Grant $7500. 2 – Off-site licenses 2 – On-site licenses | 2 Decoy 2 TBD | RPD | Targeted at identified dates in downtown area |
| Visibility of Compliance Checks | 4 | IPS | Post operations visibility |

GOAL # 2 – Responsible Beverage Service

| ACTIVITY | NUMBER PER YEAR | RESPONSIBLE PARTY | IMPLEMENTATION DATE |
| --- | --- | --- | --- |
| Responsible Beverage Service (RBS) Training SPF SIG 8,000 |  | IPS | Coordinates overall RBS - Publicize RBS training to all on-site licenses - Develop Community /downtown group to improve safety - Survey downtown bars |
| - RBS training | TBD | RPD | Redlands Police administers RBS training |
| - RBS training | TBD | IPS | IPS administers RBS training |
| Deemed Approved Ordinance (DAO) | Pending | IPS | - Support passage of DAO - Develop a media plan - Build community support for DAO |

GOAL #3 - Reduce Social Availability of Alcohol to Youth

| ACTIVITY | NUMBER PER YEAR | RESPONSIBLE PARTY | IMPLEMENTATION DATE |
| --- | --- | --- | --- |
| Nuisance party enforcement teams (10) SPF SIG funded: $8, 000 |  | RPD/ University of Redlands Police Department (URPD) |  |
| - High school party enforcement | 5 | RPD | - Graduation time – 2 - Homecoming - 3 |
| - High school party enforcement visibility San Bernardino SAPT Block grant | 5 | IPS | - Provide messages about HS party enforcement around specific high risk times - Promote timely visibility prior to operations |
| - College parties – University or Redlands | 5 | RPD/URPD | - Start of school - Greek allowed alcohol weekend - Halloween - St. Patrick’s Day - Cinco de Mayo |
| - College party enforcement visibility | 5 | IPS/University of Redlands | Develop visibility partners at U of R to reach college students with extra visibility efforts prior to nuisance patrols |
| DUI Enforcement |  |  | “Zero Tolerance” focused DUI enforcement |
| - Saturation patrols | 6 of 12 | RPD | Align with nuisance party enforcement |
| - Roadside DUI Check points | 4 of 10 | RPD | Align with nuisance party enforcement |
| - DUI Visibility | 10 | RPD/IPS | Highly visible DUI enforcement prior to the operation aligned with party enforcement visibility |
| Social Host Ordinance (SHO) San Bernardino SAPT Block grant | New | IPS | - Provide SHO training to the RPD 4/10/2013 - Develop press release on SHO enforcement training |
| SHO Visibility San Bernardino SAPT Block grant | On going | IPS | - Publicize SHO Spring 2013 (Press releases, quarterly newsletters, Op-ed before graduation, Community forum) - Presentations to HSs and parent groups - Letters to parents (May) - Promote on college campus (stakeholder meetings, attend SHO conference with U of R students) |