WORK PLAN

April 1, 2013 – March 31, 2014

Santa Barbara – Reduce Underage and Excessive Drinking in 12 – 25 Year old Age Range

GOAL1 – Reduce Retail Availability of Alcohol to Youth

| ACTIVITY | NUMBER PER YEAR | RESPONSIBLE PARTY | IMPLEMENTATION DATE |
| --- | --- | --- | --- |
| RBS training of on-premise establishments | 12 | Santa Barbara Police Department (SBPD)* | Monthly |
| Compliance checks, citations, license loss | 12 | SBPD* | Monthly |
| Inspections of on- and off-sale licensees | 12 | SBPD* | Monthly |
| Cops in shops in nightclubs | 10 | SBPD* | ~Monthly |
| Bar checks for minors | 200 | SBPD* | Weekly |
| Press releases with results of compliance checks | 12 | SBPD* | Monthly |
| Media campaign and messages targeted to retailers re: compliance checks | 8 | Council on Alcoholism and Drug Abuse (CADA), SBPD* | Monthly |
| Awareness campaign targeted to community organizations & schools | 12 | CADA | Monthly |

*Provided in-kind.

GOAL 2 - Reduce Social Availability of Alcohol to Youth

| ACTIVITY | NUMBER PER YEAR | RESPONSIBLE PARTY | IMPLEMENTATION DATE |
| --- | --- | --- | --- |
| Nuisance party patrols | As needed | SBPD* | As needed |
| Local media coverage of party patrol operations & social host liability | 6 | CADA, SBPD* | Every two months |
| Messages to parents re: social host law | 6 | CADA | Monthly |
| Community awareness campaign targeted to community organizations & schools | 12 | CADA | Monthly |

*Provided in-kind.

Santa Barbara – Reduce Alcohol-Related Motor Vehicle Crashes in 12 – 25 Year old Age Range

| ACTIVITY | NUMBER PER YEAR | RESPONSIBLE PARTY | IMPLEMENTATION DATE |
| --- | --- | --- | --- |
| Roadside DUI checkpoints | 24 | SBPD* | Every two weeks |
| Saturation patrols | 40 | SBPD* | ~ 3 times per month |
| DUI checkpoint trailer | 3 | SBPD* | Major holidays – Labor Day, New Years, Memorial Day |
| Media coverage of DUI enforcement | 12 | CADA, SBPD* | Monthly |
| Place of last drink survey, 300 DUI offenders | 1 | CADA, Zona Seca | April-May, 2013 |
| Community awareness campaign targeted to community organizations & schools | 12 | CADA | Monthly |

*Provided in-kind.

/tmp/in/input.doc