WORK PLAN

April 1,.2013 – March 31, 2014

Huntington Beach – Reduce Underage and Excessive Drinking in 12 – 25 Year old Age Range

GOAL 1 – Reduce Retail Availability

| ACTIVITY | NUMBER PER YEAR | RESPONSIBLE PARTY | IMPLEMENTATION DATE |
| --- | --- | --- | --- |
| Driving Under the Influence (DUI) Enforcement |  |  | Targeted at identified dates in downtown area and high risk party dates |
| DUI Roadside Check points Office of Traffic Safety (OTS) Safe Transportation Research & Education Center (TREC) DUI/CDL Checkpoint grant: | 11 | Huntington Beach Police Department (HBPD) | OTS Safe TREC DUI/CDL Checkpoint grant: 2 for holidays in 2013, 1 Labor Day and 8 throughout the rest of the year |
| Saturation patrols OTS S.T.E.P. Grant | 15 | HBPD | Identified dates in downtown area and a focus on underage party dates and places` |
| Saturation patrols SPF SIG | 8 | HBPD | Identified dates in the downtown area |
| DUI Visibility | 34 | HBPD / Community Service Programs, Inc. (CSP) | Timely visibility before the DUI operations for deterrence and post operation with results |
| Department of Alcoholic Beverage Control (ABC) Compliance Enforcement – ABC grant (10) operations |  |  |  |
| Undercover operation in downtown business district | 2 | HBPD | TBD |
| Minor Decoy | 2 | HBPD | TBD |
| Undercover operation for service to overly intoxicated customers | 2 |  | TBD |
| Shoulder tap operations | 2 | HBPD | TBD |
| “Trap Door” operations (minors using false ID’s) | 2 | HBPD | TBD |
| Visibility of Compliance Checks | 10 | HBPD/CSP | Post operations visibility |
| Electronic Sign | As needed | HBPD | Timely visibility of DUI operations |

Goal #2 responsible Beverage Service and Enforcement

| ACTIVITY | NUMBER PER YEAR | RESPONSIBLE PARTY | IMPLEMENTATION DATE |
| --- | --- | --- | --- |
| Responsible Beverage Service (RBS) and Enforcement |  |  |  |
| RBS Training – 2 Leads Trainings (ABC Grant) | 2 | ABC/HBPD | HBPD has two Leads trainings to conduct at part of ABC grant. CSP will assist in inviting bar employees to participate TBD |
| Private Security Officer (PSO) training for bouncers (mandatory state training) | As needed |  |  |
| RBS - bar manager and owner training By Gregg Hanour prior bar owner | 2 | CSP | CSP will arrange the 3 hour training with bar owners and managers TBD |
| See ABC compliance enforcement for list of undercover and “Trap Door” operations | 6 | HBPD |  |
| Downtown office HBPD business district deployment of officers | Everyday | HBPD | 2 – 5 officers every evening in the downtown area Foot and vehicle patrol |
| RBS Foot Patrols trained in dealing with intoxicated patrons, and ABC laws to monitor Compliance | 8 | HBPD | Target identified dates in downtown area RBS foot patrol officers will patrol the downtown bar area looking for ABC code violations, over service, underage access |
| Entertainment permit has a provision for mandatory RBS training of staff | For each permit | HBPD/CSP | Arrangements will be made for RBS training for licensees with entertainment permit’s staff RBS training tracking |
| City Council Resolution established a Conditional Use Permit (CUP) for new alcohol licenses | Passed | HBPD | HBPD can place conditions on new or modified alcohol licenses. Officers trained to enforce resolution |
| Deemed Approved Ordinance (DAO) HBPD is exploring the pros and cons of passing the ordinance | Pending | HBPD/CSP | DAO would allow for conditions to be placed on problem alcohol licenses (missing part of CUP) |

GOAL 3 - Reduce Social Availability of Alcohol to Youth

| ACTIVITY | NUMBER PER YEAR | RESPONSIBLE PARTY | IMPLEMENTATION DATE |
| --- | --- | --- | --- |
| Nuisance party enforcement team 2 officers assigned specifically to focus on party calls | 8 | HBPD | At identified party dates e.g. graduation / homecoming Cinco de Mayo, July 4th and collaborate with HBPD to create schedule |
| Visibility of nuisance party enforcement teams | Align with operations | CSP | Additional visibility to students prior party enforcement dates using social media, school newspaper, newsletters, email blasts to parents |
| Social Host Liability law | New | CSP/HBPD | Officers trained in Social Host Ordinance (SHO) enforcement; Enforce during Nuisance party enforcement and call for service |
| Visibility of Social Host Liability | On going | CSP | Educate parents and students on new SHO and promote with timely enforcement |
| DUI Enforcement Saturation patrols | See DUI enforcement | HBPD | Schedule saturations patrols on identified dates and align with nuisance party enforcement |
| Compliance checks off-site retail outlets | 4 | HBPD | Decoy (2) and Shoulder tap (2) operations focus on retail availability |
| Visibility of Compliance Checks | 4 | CSP | Post compliance operation visibility |